FERABEE EXECUTION BLUEPRINT
OPERATIONAL ROADMAP & COMPLIANCE ARCHITECTURE
CONFIDENTIAL - INTERNAL DISTRIBUTION ONLY

► PHASE 1: INCORPORATION & GOA MANUFACTURING SETUP (MONTHS 1-2)

[COMPLETED] FeraBee Liquor Pvt Ltd RoC Company Registration.

[COMPLETED] Trademark filing for 'FeraBee', 'The Royal Bee', and 'Hexagonal Logo'.

[CRITICAL] Finalize Third-Party Lease Bottling Agreement in Goa (Verna/Ponda).

[PENDING] Submit FL-9 Label Registrations for 6 Core SKUs to Goa State Excise.

[CRITICAL] Procure initial Glassware molds and custom black spray-coated bottles.

► PHASE 2: MAHARASHTRA IMPORT & LOGISTICS PIPELINE (MONTHS 2-3)

Establishing the supply chain corridor from Goa bottling plant to Maharashtra State Excise warehouses.

| Action Item | Regulatory Authority | Timeline | Status |
| --- | --- | --- | --- |
| Apply for FL-1 Wholesale License (MH) | Maharashtra State Excise | Week 6 | Pending |
| Secure Bonded Warehouse (Pune/Thane) | MH Excise & Fire Dept | Week 8 | In Progress |
| Register Goa Labels for MH Import | Bhavan Excise Office, Mumbai | Week 9 | Pending |
| Establish Transport Pass (TP) Protocol | Inter-State Border Checkposts | Week 10 | Pending |

► PHASE 3: FLAGSHIP LOUNGE LAUNCH (MONTHS 3-4)

Rollout of the first 3 Company Owned Company Operated (COCO) lounges to prove unit economics.

[CRITICAL] Lease signing: Pune (FC Road), Thane (Ghodbunder), Panjim (Tiswadi).

[PENDING] FL-3 Bar License Application & Local Police NOC.

[PENDING] Interior Fit-out: Hexagonal ceiling, Black Marble, 3D Bee feature wall.

[PENDING] Procure RFID Wristband POS system and 60ml Electronic Auto-Pourers.

[PENDING] Hire & Train: 14 Staff Members per outlet (Mixologists, Chefs, Servers).

► PHASE 4: FRANCHISE EXPANSION (MONTHS 5-36)

Aggressive scale-up to 367 Taluka Lounges targeting 1 Lounge per Taluka (15km Exclusivity).

| Milestone | Cumulative Outlet Count | Target Gross Revenue Run-Rate |
| --- | --- | --- |
| Month 6: Tier-1 Talukas Live | 25 Lounges | ₹12.7 Crore / Month |
| Month 12: Western MH & Goa Complete | 100 Lounges | ₹50.8 Crore / Month |
| Month 24: Deep Maharashtra Penetration | 200 Lounges | ₹101.7 Crore / Month |
| Month 36: Full State Coverage (Exit Phase) | 367 Lounges | ₹186.6 Crore / Month |

► TECHNOLOGY & SECURITY INFRASTRUCTURE

Mandatory systems installed in every Franchise Lounge to enforce the 61% Gross Profit standard:

| System | Vendor / Spec | Operational Purpose |
| --- | --- | --- |
| Smart POS & Billing | PetPooja / Posist | Tracks 'Unlimited Package' time limits (Silver/Gold/Plat) |
| IoT Auto-Pourers | Berg / Exacta | Dispenses exact 60ml pegs; linked to POS to prevent bartender theft |
| RFID Wristbands | Custom NFC Tags | Customer entry/exit tracking and table assignments |
| AI Cloud CCTV | Hikvision / Wipro | 16-Camera HD tracking Kitchen Pass & Bar counter |